## SWE 573
Create professional Gantt charts in GanttPRO in a few clicks
SWE 573 | [10 empty] | 2020-04-28 14:57
Color | WBS Number |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Cost | Actual cost | Created | Creator | Type | Project | Level
| 1 | Implementation |  |  |  | 2020-05-02 12:00 | 2020-05-23 15:00 |  | 0 | 38 | 0 | 0 |  |  |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | project | SWE 573 | 1
| 1.1 |  | Deployment |  |  | 2020-05-17 12:00 | 2020-05-23 15:00 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | task | SWE 573 / Implementation | 2
| 1.2 |  | Training |  |  | 2020-05-02 12:00 | 2020-05-17 17:00 |  | 0 | 34 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | task | SWE 573 / Implementation | 2
| 1.3 |  | Development/Implementation Completed |  |  | 2020-05-23 12:00 | 2020-05-23 12:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | milestone | SWE 573 / Implementation | 2
| 2 | QA |  |  |  | 2020-05-02 10:00 | 2020-05-30 12:00 |  | 0 | 50 | 0 | 0 |  |  |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | project | SWE 573 | 1
| 2.1 |  | Unit Test |  |  | 2020-05-02 10:00 | 2020-05-23 12:00 |  | 0 | 38 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | task | SWE 573 / QA | 2
| 2.2 |  | Function Test |  |  | 2020-05-02 10:00 | 2020-05-23 12:00 |  | 0 | 38 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | task | SWE 573 / QA | 2
| 2.3 |  | Integration Test |  |  | 2020-05-02 10:00 | 2020-05-17 17:00 |  | 0 | 36 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | task | SWE 573 / QA | 2
| 2.4 |  | Regression Test |  |  | 2020-05-10 10:00 | 2020-05-30 12:00 |  | 0 | 32 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | task | SWE 573 / QA | 2
| 2.5 |  | System Test |  |  | 2020-05-10 10:00 | 2020-05-16 12:00 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | task | SWE 573 / QA | 2
| 2.6 |  | User Acceptance Test |  |  | 2020-05-10 10:00 | 2020-05-16 12:00 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | task | SWE 573 / QA | 2
| 2.7 |  | Test Completed |  |  | 2020-05-23 10:00 | 2020-05-23 10:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | milestone | SWE 573 / QA | 2
| 3 | Operations & Maintenance |  |  |  | 2020-05-23 15:00 | 2020-05-31 15:00 |  | 0 | 18 | 0 | 0 |  |  |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | project | SWE 573 | 1
| 3.1 |  | Operations Activities |  |  | 2020-05-23 15:00 | 2020-05-24 17:00 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | task | SWE 573 / Operations & Maintenance | 2
| 3.2 |  | Maintenance Activities |  |  | 2020-05-23 15:00 | 2020-05-30 17:00 |  | 0 | 14 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | task | SWE 573 / Operations & Maintenance | 2
| 3.3 |  | Operations & Maintenance Completed |  |  | 2020-05-31 15:00 | 2020-05-31 15:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | milestone | SWE 573 / Operations & Maintenance | 2
| 4 | Disposition |  |  |  | 2020-05-31 15:00 | 2020-06-28 12:00 |  | 0 | 46 | 0 | 0 |  |  |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | project | SWE 573 | 1
| 4.1 |  | Archive |  |  | 2020-05-31 15:00 | 2020-06-14 17:00 |  | 0 | 26 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | task | SWE 573 / Disposition | 2
| 4.2 |  | Disposal |  |  | 2020-06-20 10:00 | 2020-06-28 12:00 |  | 0 | 20 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | task | SWE 573 / Disposition | 2
| 4.3 |  | Project Completed |  |  | 2020-06-28 12:00 | 2020-06-28 12:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:20 | Esma Özelbaş | milestone | SWE 573 / Disposition | 2
| 5 | Implementation Details |  |  |  | 2020-05-02 10:00 | 2020-05-17 17:00 |  | 0 | 36 | 0 | 0 |  |  |  | 0 | 0 | 2020-04-28 12:47 | Esma Özelbaş | project | SWE 573 | 1
| 5.1 |  | Database |  |  | 2020-05-02 10:00 | 2020-05-03 17:00 |  | 0 | 12 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:47 | Esma Özelbaş | task | SWE 573 / Implementation Details | 2
| 5.2 |  | Backend |  |  | 2020-05-02 10:00 | 2020-05-10 17:00 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:48 | Esma Özelbaş | task | SWE 573 / Implementation Details | 2
| 5.3 |  | Frontend |  |  | 2020-05-09 10:00 | 2020-05-17 17:00 |  | 0 | 24 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 12:48 | Esma Özelbaş | task | SWE 573 / Implementation Details | 2
| 5.4 |  | Milestone-1: Backend and API Support |  |  | 2020-05-09 10:00 | 2020-05-09 10:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:53 | Esma Özelbaş | milestone | SWE 573 / Implementation Details | 2
| 5.5 |  | Milestone-2: Frontend |  |  | 2020-05-17 10:00 | 2020-05-17 10:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:53 | Esma Özelbaş | milestone | SWE 573 / Implementation Details | 2
| 6 | Feature Implementation |  |  |  | 2020-05-02 10:00 | 2020-05-16 17:00 |  | 0 | 30 | 0 | 0 |  |  |  | 0 | 0 | 2020-04-28 17:44 | Esma Özelbaş | project | SWE 573 | 1
| 6.1 |  | Account |  |  | 2020-05-02 10:00 | 2020-05-03 17:00 |  | 0 | 12 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:44 | Esma Özelbaş | task | SWE 573 / Feature Implementation | 2
| 6.2 |  | Homepage |  |  | 2020-05-02 10:00 | 2020-05-03 17:00 |  | 0 | 12 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:48 | Esma Özelbaş | task | SWE 573 / Feature Implementation | 2
| 6.3 |  | User Profile |  |  | 2020-05-02 10:00 | 2020-05-09 17:00 |  | 0 | 18 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:45 | Esma Özelbaş | task | SWE 573 / Feature Implementation | 2
| 6.4 |  | User Homepage |  |  | 2020-05-02 10:00 | 2020-05-09 17:00 |  | 0 | 18 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:45 | Esma Özelbaş | task | SWE 573 / Feature Implementation | 2
| 6.5 |  | Search |  |  | 2020-05-09 10:00 | 2020-05-10 11:00 |  | 0 | 7 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:44 | Esma Özelbaş | task | SWE 573 / Feature Implementation | 2
| 6.6 |  | Recommendation |  |  | 2020-05-09 10:00 | 2020-05-10 17:00 |  | 0 | 12 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:44 | Esma Özelbaş | task | SWE 573 / Feature Implementation | 2
| 6.7 |  | Follow/Like/Dislike |  |  | 2020-05-09 10:00 | 2020-05-10 17:00 |  | 0 | 12 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:45 | Esma Özelbaş | task | SWE 573 / Feature Implementation | 2
| 6.8 |  | Posts - Recipes |  |  | 2020-05-09 10:00 | 2020-05-09 17:00 |  | 0 | 6 | 0 | 0 |  |  |  | 0 | 0 | 2020-04-28 17:45 | Esma Özelbaş | tasks group | SWE 573 / Feature Implementation | 2
| 6.8.1 |  |  | Create a recipe |  | 2020-05-09 10:00 | 2020-05-09 17:00 |  | 0 | 6 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:47 | Esma Özelbaş | task | SWE 573 / Feature Implementation / Posts - Recipes | 3
| 6.8.2 |  |  | Remove a recipe |  | 2020-05-09 10:00 | 2020-05-09 17:00 |  | 0 | 6 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:47 | Esma Özelbaş | task | SWE 573 / Feature Implementation / Posts - Recipes | 3
| 6.9 |  | Posts - Comments |  |  | 2020-05-09 10:00 | 2020-05-09 17:00 |  | 0 | 6 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:45 | Esma Özelbaş | task | SWE 573 / Feature Implementation | 2
| 6.10 |  | Posts - Nutritional Value |  |  | 2020-05-09 10:00 | 2020-05-10 17:00 |  | 0 | 12 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:46 | Esma Özelbaş | task | SWE 573 / Feature Implementation | 2
| 6.11 |  | Posts - Tagging |  |  | 2020-05-10 10:00 | 2020-05-10 17:00 |  | 0 | 6 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:46 | Esma Özelbaş | task | SWE 573 / Feature Implementation | 2
| 6.12 |  | Tracking Nutritional Value |  |  | 2020-05-10 10:00 | 2020-05-10 17:00 |  | 0 | 6 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:46 | Esma Özelbaş | task | SWE 573 / Feature Implementation | 2
| 6.13 |  | Reporting |  |  | 2020-05-16 10:00 | 2020-05-16 17:00 |  | 0 | 6 | 0 | 0 | Open | Medium |  | 0 | 0 | 2020-04-28 17:46 | Esma Özelbaş | task | SWE 573 / Feature Implementation | 2
This document has been created with the help of https://ganttpro.com online service